## Slide 1: Project Progress Group 6 Budget Buddy
Group Members:
Jasleen Minhas [202481225] – Group Lead
Masroor Rahman [202482239]
Sumaiya Khan [202480995]
Joel George Sam [202483190]
Kaustubh Patil [202580621]
Ronit Gajjar [202488048]
COMP 6905 Software Engineering
(Finance Tracking WebApp)

## Slide 2: INDEX
Summary of the Project
Progress to Date
  Completed Work
  Delivered Artifacts
Glimpses of our project so far
Challenges and Solutions
Next Steps
  Goal for the Next Phase
  Adjustment to the Plan
Updated Timeline
Updated Team Members progress
Live Demo of the Project Progress

## Slide 3: SUMMARY OF THE PROJECT

## Slide 4
BUDGET BUDDY
Overview of the Project:
  Budget Buddy is a personal expense management web application.
  Helps users track, visualize, and manage their spending efficiently.
  Built with React (frontend) and Firebase (backend & database).
Key Features:
  Login and Signup authentication
  Add, Edit, Delete Expenses easily
  Categorize Transactions for better organization
  Interactive Dashboards & Charts for expense insights
  Export Reports as PDF for record keeping and sharing
  Responsive Design optimized for mobile and desktop

## Slide 5
  Tech Stack: Reactjs + Firebase
  Methodology: Agile (5 Sprints, 2 weeks each)
  Live App: Budget Buddy Live
  CI/CD: Setup completed and deployment live on Vercel

## Slide 6: Progress to Date

## Slide 7: Progress to Date (Iteration 1–2)
Iteration 1 (Sept 22 – Oct 5): Setup & Requirements - ✅ Completed
GitHub repo setup, team roles, requirements gathering, UML diagrams, Firebase project setup
Artifacts: Requirement docs, UML diagrams
Iteration 2 (Oct 6 – Oct 19): Authentication & Deployment - ✅ Completed
Login/Signup/Logout, Firebase Auth, Landing Page, CI/CD setup & deployment
Artifacts: Auth screens, Landing page, Unit tests, Deployment Logs, Live app

## Slide 8: Progress to Date (Iteration 3–4)
Iteration 3 (Oct 20 – Nov 2): Expense & Category Management - 🟡 Partially Completed
Expense CRUD, Firebase integration, unit tests
Artifacts: Expense page Completed, Category page in progress
Iteration 4 (Nov 3 – Nov 16): Dashboard & Reporting - ⏳ Planned
Dashboard layout, charts, expense summary, PDF/CSV export, unit tests
Artifacts: Dashboard Mockups, Report Generation Planned

## Slide 9: GLIMPSES OF OUR PROJECT SO FAR

## Slide 10: Class and Use case diagram (Done in the Requirements phase)

## Slide 11: LANDING PAGE

## Slide 12: lOGIN AND SIGNUP PAGE

## Slide 13: Expenses page

## Slide 14: Adding an expense

## Slide 15: firebase
The image depicts a Firebase user management interface showing email addresses, providers, creation dates, sign-in dates, and unique user IDs.

## Slide 16: Challenges faced in the initial iterations AND proposed SOLUTIONs to those

## Slide 17
Challenge | Description | Solution
GitHub Collaboration | Difficulties managing commits/branches | Team session + branching guide from Github
Wrong Commits/Merge Conflicts | Overlapping work caused issues | Peer review policy
Working on Main Branch | Accidental direct commits | Protected the main branch, Just the team lead can do that
Wrong Issue References | Incorrect issue numbers in commits | Standard commit message format + Pair programming
Code Crashes | Integration errors | Local testing before commits
Task Coordination | Aligning timelines | GitHub Projects + weekly sync meetings

## Slide 18: Next steps

## Slide 19: Next steps
Complete Category Management Page
Dashboard visualization (Chart.js: Pie & Bar charts)
Report export (PDF/CSV using jsPDF + html2canvas)
Budget Summary Section (monthly totals, category stats)
Integration & regression testing
Finalize documentation & presentation slides

## Slide 20: Adjustments to Plan
CI/CD integrated earlier
Live deployment on Vercel
Auto-deploy on
main branch pushes

## Slide 21: Updated Timeline The issues we have completed and in progress

## Slide 22
Our Github Planning board
Iteration 1 and 2 issues are all completed

## Slide 23
Iteration 3 is in progress
Iteration 4 will start from Nov 3rd

## Slide 24: Updated TEAM MEMBER RESPONSIBILITIES PROGRESS

## Slide 25
Member | Role | Key Contributions | Progress
Jasleen | Project Lead, Frontend, Testing | Repo setup, Requirements, Auth, Landing, Expense Module, Unit Tests, Deployment | 🟢 100%
Mashroor | Firebase & CI/CD | Firebase setup, Auth integration, Logout/session handling, Deployment | 🟢 100%
Sumaiya | UI/UX Design | Landing page design, Auth UI, Branding | 🟢 100%
Joel | Testing & Firebase | Unit tests, Firebase validation | 🟢 100%
Ronit | Backend & Expense | Expense CRUD, Firebase integration | 🟢 100%
Kaustubh | Frontend (Expense) | Expense UI, CRUD operations | 🟢 100%

## Slide 26: Summary of Progress
Sprints 1–2: Fully completed (setup, authentication, CI/CD) - ✅ Completed
Sprint 3: Expense module functional & tested; Category management - 🟡 Partially Completed
Sprint 4: Dashboard & reporting started; visualization and export upcoming – ⏳ Planned
Sprint 5: System testing and Fix the bugs, Final documentation - ⏳ Planned
Next Focus: Analytics dashboard, report export, final integration testing

## Slide 27: LIVE demo of the PROJECT progress
https://budget-buddy-mun.vercel.app/

## Slide 28: Thank you any question?